## Sheet1
[Version: 2020-08-28] | [6 empty] | Architect/Consultant Logo and Address
TO: | Board of Education of School District No. 36 (Surrey)
Capital Project Office
14033 - 92nd Avenue
| Surrey, B.C. V3V 0B7 |  |  |  | Certificate No:
Project Name: |  | Mechancial Upgrade Ph 2 - ABC Secondary School - Site # 123
SD36 Project Number: |  | 08-168-003 (sample) |  |  | Date:
This certificate entitles |  |  |  |  | Amount: |  | 57750
to a payment in the amount of | [5 empty] | 00/100 dollars including taxes.
in accordance with the contract for the above project, as shown on the attached Progress Claim
Statement of Contract |  |  |  | Statement of Certificate of Payments
Original Contract Price (no taxes) |  |  | 760000 | Work Completed |  |  | 550000
Contract changes: |  |  |  | Less Builder's Lien Holdback |  |  | 45000
| Additions to C.O. No | 0000-00 | 100000 | Less Deficiency Holdback |  |  | 0
| Credits to C.O. No | 0000-00 | 75000 | Total Certified to Date |  |  | 505000
Revised Contract Amount |  |  | 785000 | Less Previously Certified |  |  | 450000
Statement of Lien Holdbacks |  |  |  | Certificate Payable |  |  | 55000
Builder's Lien Holdback @ 10% |  |  | 55000 | G.S.T. @5% |  |  | 2750
Less Early Release of Lien holdback |  |  | 10000 | Total Certificate Payable |  |  | 57750
Less Current Lien Holdback Release |  |  | 0 | Certified to Date |  |  | 505000
Builder's Lien Holdback Retained |  |  | 45000 | Contract Balance |  |  | 280000
294000
This certificate is based on observations made during period visits to the site
and the data comprising the contractor's application for payment and not on a
Per |  |  |  | detailed and exhaustive examination of quantities and quality of materials
| Prime Architect/Consultant |  |  | installed and labour extended in the work. Certificate of Payment does not
guarantee the Work is correct or complete.
For School District Use Only
Project Manager: |  |  |  | Date:
Funding Approval: |  |  |  | Date:
Lien Clearance Received: |  |  |  | Date:
Work Safe BC Clearance: |  |  |  | Date:
Statutory Declaration Received: |  |  |  | Date: