## Sheet1
Note: Do not enter values in red colored cells - they are formulated.
| BOARD OF EDUCATION OF | [5 empty] | [Version 2021 07 30]
SCHOOL DISTRICT NO. 36 (SURREY)
CHANGE ORDER
CONSULTANT: | ABC Consultants |  |  | SCHOOL NAME: | ABC Secondary - Site #123
REFERENCE NO.: | 403-031 |  |  | SD36 PROJ. NO.: | 07-168-006 (Mech Upgrade Ph 3)
CONTRACTOR: | DEF Contractor Ltd. |  |  | DATE: | November 5, 2007
|  |  |  | CHANGE ORDER NO.: |  | 002
Reference Contemplated Change Order or Change Directive if applicable: |  |  |  |  | CCO NO.: | 004
Pursuant to paragraph 6.2.2 of GC 6.2 - CHANGE ORDER in CCDC 2 - 2008, the following is an amendment to the Contract stating the agreement between the Owner and the Contractor upon a change in the Work and the adjustments in the Contract Price and Contract Time:
(attach Contractor's quotation)
- used less …. than originally planned | [6 empty] | -150
- did not require …. | [6 empty] | -50
-
-
QUOTED PRICE FOR THIS CHANGE ORDER: |  |  | EXTRA | OR | (CREDIT) |  | -200
Enter credit as negative amount ( $ ) |  |  |  | (Circle One)
CONTRACT TIME IS INCREASED / DECREASED BY |  |  |  | 1
| (Circle One) |  |  | WORKING DAYS
REASON FOR CHANGE:
Original Contract Price (No GST) | [6 empty] | 5000
|  | EXTRAS |  | CREDITS
Previous change orders |  | 100 |  | 0
THIS CHANGE ORDER |  |  |  | -200
TOTAL Change Orders |  | 100 |  | -200
Revised Contract Price (No GST) | [6 empty] | 4900
DO NOT PROCEED until signed by School District No. 36 (Surrey)
Please sign all copies and return:
Recommended by Consultant |  | Date |  | Recommended by Project Manager |  |  | Date
School District No. 36 (Surrey)
Approved by Contractor |  | Date |  | Approved by Owner |  |  | Date
Secretary-Treasurer, School District No. 36 (Surrey)
DISTRIBUTION: White: SD36 / Yellow: Architect or Consultant / Blue: Contractor / Green: Project Manager
sample only